Chapter 17: Work Breakdown Structure (WBS) (FPM2ed p.206)

1. Body of Knowledge Mapping

2. Product Breakdown Structure (PBS)

3. Work Breakdown Structure (WBS)

4. WBS Dictionary

5. Location Breakdown Structure

6. Transport Breakdown Structure

7. Cost Breakdown Structure (CBS)

8. Numbering System

9. WBS Templates

10. Spreadsheet Presentation

The following questions have been designed to test your knowledge of the chapter and prompt discussion. Please note that each question could have one or more correct answers.

17.1: Which one of the following is a WBS? (FPM2ed p.206)

a. A WBS is the Women’s Breakdown Service.

b. A WBS is the Western Breakdown Structure.

c. A WBS is the Work Breakdown Service.

d. A WBS is the Work Breakdown Structure.

17.1 Answer: D is correct. The WBS subdivides the project into a number of manageable work packages. A, B and C are incorrect.

17.2: Which three of the following outline the purpose of a Work Breakdown Structure (WBS)?

a. To subdivide the project work into smaller and more manageable items of work.

b. To define the complete scope of work.

c. To define the work that is not included in the project.

d. To define the logical sequence between the work packages and to identify dependencies.

17.2 Answer: A, B and C are correct. The WBS is a structured methodology to quantify the full scope of work and, by implication, what is not included. D is incorrect as the WBS does not show the logical sequence of when work should be performed.

17.3: Which one of the following is a PBS? (FPM2ed p.208)

a. A PBS is the People Breakdown Service.

b. A PBS is the Project Breakdown Structure.

c. A PBS is the Process Breakdown Structure.

d. A PBS is the Project Business Service.

17.3 Answer: B is correct. In the project management context, the PBS enables the project manager to break down the project into a number of deliverables. A, C and D are incorrect.

17.4: Which three of the following relate to the PBS (Product Breakdown Structure)? (FPM2ed p.208)

a. The PBS is a method of breaking down the project into deliverables.

b. The PBS is a method used to confirm the configuration of the deliverables work together.

c. The PBS / WBS interface is used to identify the work to make the deliverables.

d. The PBS helps identify the deliverables’ dependencies.

17.4 Answer: A, B and C are correct. The PBS subdivides the project into deliverables that can then be further subdivided into work packages. D is incorrect as there is no logical relationship between the deliverables – these will be developed in the network diagram.

17.5: Which two of the following relate to Work Packages? (FPM2ed p.211)

a. The project work is delivered by courier as a package.

b. There is a time based logical relationship between the work packages.

c. A work package is a means of subdividing the scope of work into manageable units of work.

d. The WBS is used to subdivide the project into a number of work packages.

17.5 Answer: C and D are correct. A and B are incorrect as there is no time based logical relationship between work packages.

17.6: Which two of the following outline the difference between a WBS Work Package and an Activity list?

a. They are both the same.

b. Work packages are items of work and are time based.

c. Activities are an input into the CPM.

d. Activities are logically related.

17.6 Answer: C and D are correct. A and B are incorrect.

17.7: Which two of the following relate to the WBS Dictionary? (FPM2ed p.211)

a. The WBS dictionary contains all the information the project manager needs to complete the project.

b. By using a breakdown structure the level of detail can be adjusted to meet the required level of information.

c. The WBS dictionary ensures that the project terminology spelling is correct.

d. The WBS dictionary enables the scope of the project to creep into the time available.

17.7 Answer: A and B are correct. The WBS dictionary lists all the items of work. C and D are incorrect.

17.8: Which three of the following relate to the Numbering of the WBS work packages? (FPM2ed p.216)

a. The numbering system uniquely identifies all the work packages.

b. All work packages should have a number even if it is the project number.

c. If the work packages are numbered then the purchase orders can be numerically linked to the associated work package.

d. If the work packages are uniquely numbered then accounts can be numerically linked to the associated work package.

17.8 Answer: A, C and D correct. The numbering system enables all the work packages to be uniquely identified, which means other parameters can be linked such as purchase orders and accounts. B is incorrect as the different work packages should have a different number to each other so that they can be uniquely identified.

17.9: Which two of the following relate to a WBS Template? (FPM2ed p.217)

a. A WBS template can be used when two projects have similar organization structures.

b. A WBS template can be used when the current project uses a breakdown similar to a previous project.

c. A WBS template is a structured template that can be used as a prompt or checklist.

d. A WBS template is a network diagram used by a previous project.

17.9 Answer: B and C are correct. Using a proven WBS template is a sensible starting point as it is always easier to adjust a proven format rather than start from a blank sheet of paper. A and D are incorrect.

17.10: Which two of the following relate to a WBS Spreadsheet? (FPM2ed p.218)

a. A WBS spreadsheet is popular type of software used to present project information in a tabular format.

b. A WBS spreadsheet is a format that helps to build up a complete list of work packages.

c. A WBS spreadsheet can be used to calculate the start and finish dates of all the activities.

d. A WBS spreadsheet can be used to calculate dependencies.

17.10 Answer: A and B are correct. A spreadsheet with the WBS as the anchor column can be used to present a wide range of project parameters. C and D are incorrect as the CPM calculates the start and finish dates, and dependencies.